## Project Data
FDOT Project Data
Project | Regional Integrated Corridor Management System
Project Manager | Tushar Patel
R&C Category | 2
Project # | BE521
Sponsor | FDOT District 5 Traffic Operations
Vendor | SwRI
Vendor PM | Robert Heller
Vendor Project # | 23368
Project Award | 2018-03-14
Project End | 2023-03-13
Project NTP | 2018-03-14
Change Log
Date of Change Changed By | Description of Change
May 5, 2018 Robert Heller | After review by FDOT and indication that structure is approved (Clay Packard email), revised version to 1.0
May 4, 20119 | Heller revised the Risk tab to have separate columns for risk impact and risk strategy.

## Change Control
Change Control Log
Project |  | Regional Integrated Corridor Management System |  |  | Project # |  |  | BE521
Project Manager |  | Tushar Patel |  |  | Sponsor |  |  | FDOT District 5 Traffic Operations
R&C Category |  | 2 |  |  | Worksheet Updated
Change Control Number | Change Description | Priority (H, M, L) | Originator | Date Entered | Change Owner | Date Assigned | Date Due | Scope Change? Y / N Describe | Cost Change? Y / N Describe | Schedule Change? Y / N Describe | Event Driven R&C Category | Risk Log # | Issue Log # | Decision Log # | Action Item Log # | Requirement # | Date Presented | Approval Authority | Approval Status | Date of Decision | Requires Contract Amendment? | Date of Contract Amendment | Link to Change Control Form
1 | Process the ARBM data to create unique geometries for the bi‐directional links with link‐ids matching those of the ITSIQA data. The unique geometries will be created by offsetting the end-points and mid-points of the ARBM uni-directional links by some appropriate amount. | H | Robert W. Heller | 2019-04-23 | SwRI | 2019-04-23 |  | Y | Y | N | [6 empty] | 2019-04-23 |  | No approval
2
3
4
5
6
7
8
9
10
11
12
This is largely unknown until somebody looks at the data.
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | 2019-06-04 | Email |  | Heller | Patel / Dilmore | No
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | 2019-06-14 | Email |  | Heller | Patel / Packard | No

## Risk Log
Risk Management Log
Project |  | Regional Integrated Corridor Management System |  |  | Project # |  |  | BE521
Project Manager |  | Tushar Patel |  |  | Sponsor |  |  | FDOT District 5 Traffic Operations
R&C Category |  | 2 |  |  | Worksheet Updated |  |  | 2019-07-01
Risk # | Risk Description | Date Entered | Identified By | Probability | Impact | Score Highest = 16 | Priority (H, M, L) | Tolerance (H, M, L) | Impacts |  |  |  | Strategy |  |  |  | Risk Mitigation / Response Description | Risk Owner | Review Cycle | Status | Date Closed |  |  |  |  | Comments | Risk Realized - Mitigation / Contingency Activities Taken
[9 empty] | Schedule | Cost | Scope | Quality | Avoidance | Transfer | Mitigation | Acceptance | [5 empty] | Actiion Log # | Issues Log # | Decision Log # | Change Control Log #
1 | Withdrawl of Stakeholder Support | 2018-04-10 | Robert Heller | 1 | 3 | 3 | L | L |  |  |  | ü |  |  | ü |  | FDOT has assumed the role for stakeholder management. Commitment from the stakeholders to the project needs to be cultivated and monitored. | FDOT | Monthly | Stable | [5 empty] | I classified it as a quality risk because withdrawl of stakeholder support can cause lack of ability to adjust response plan signal timing plans.
2 | Lack of availability of data sources | 2018-04-10 | Ron Flammia | 4 | 4 | 16 | H | L | ü | [5 empty] | ü |  | Claudia Paskauskas has been assigned to gather information about the data sources, including protocols, data formats and availability. This information should be used to accurately assess the risk associated with each data sources. | FDOT | Weekly | Closed | 2019-04-04 |  |  |  |  | Will track these individually not together.
3 | Modeling Engine is not available during Iteration 4. | 2018-04-10 | David Vickers | 1 | 4 | 4 | L | L | ü |  |  |  |  | ü |  |  | The schedules of the two contracts needs to be carefully monitored to facilitate coordination between them for integration testing and acceptance testings. | FDOT | Quarterly | Closed | 2021-04-01 |  |  |  |  | Responsibility for the modeling engine was removed from BE521 and placed in a separate contract. This creates schedule risk between the two contracts. 11/14/2018: SwRI was told that the Modeling Engine selected vendor should receive an NTP on or about 11/14, about 6 months later than originally projected. It may at this time be advantageous to begin the process of coordinating schedules between the two contracts. 01/22/2019 there will be a static version of the model and data available to test against. This should reduce risk.
4 | Modeling Engine interface definition. Modeling Engine Vendor interface will not match the R-ICMS APIs. Traffic conditions, Events, DMS APIs will be defined during Iteration 2 and the Modeling Engine Vendor NTP will likely occur during Iteration 2 development. | 2018-04-10 | Robert Heller | 1 | 3 | 3 | L | L |  | ü | [5 empty] | ü | BE521 will define APIs for accessing the data within the DFE. Need to sync this early with the expectations of the ME to make the two work. | FDOT | Quarterly | Closed | 2021-04-01 |  |  |  |  | Responsibility for the API definitions was squarely laid on the DFE developer, but not representated that way to the ME provider. This needs to be worked out early in the contract to avoid rework. | Closing as SwRI and AIMSUN are currently working out these APIs for use by SOT and ERE.
5 | Mezoscopic Traffic Model availability | 2018-04-10 | Robert Heller | 4 | 1 | 4 | L | H | ü | [5 empty] | ü |  | Monitor the development of the Mezoscopic Traffic Model to insure it will be ready for integration testing. | FDOT | Quarterly | Closed | 2021-04-01 |  |  |  |  | The development schedule of the Mezoscopic Traffic Model needs to sync with the availability of the ME and the development of the DFE and DSS to get everything to work. 01/22/2019 there will be a static version of the model and data available to test against. This should reduce risk. | Will use the UCF traffic model temporarily.
6 | Format for ERE rules need to be available prior to developing the ERE. | 2018-04-10 | David Vickers | 1 | 2 | 2 | L | H |  | ü | [5 empty] | ü | SwRI and FDOT (Kapsch) need to coordinate this early to avoid schedule and cost imacts. | SwRI | Monthly | Closed | 2019-04-04 |  |  |  |  | This meeting did not occur. Needs to be rescheduled for a teleconference when Matt Juckes returns from Australia. No change to severity. (RWH 5/3/2018) Currently a coordination meeting is to take place during the Requirements Walkthrough week. Need to insure that happens. 11/14/2018: As we have met with Kapsch traffic engineers, it appears that the rules are going to be of a global nature and not related to individual corridors. Clay 11/15> Please provide meeting notes RWH 1/7/2019 Occurred during Iteration 1 CDR.
7 | Format for DSS response plans and response plan elements. | 2018-04-10 | David Vickers | 1 | 4 | 4 | L | H |  | ü | [5 empty] | ü | SwRI and FDOT (Kapsch) need to coordinate this early to avoid schedule and cost imacts. | SwRi | Monthly | Closed | 2021-04-01 |  |  |  |  | This meeting did not occur. Needs to be rescheduled for a teleconference when Matt Juckes returns from Australia. No change to severity. (RWH 5/3/2018) Currently a coordination meeting is to take place during the Requirements Walkthrough week. Need to insure that happens. 12/4/2018: R-ICMS will retrieve this data from ArcGIS. Still need to look at the API for retrieving this data and the format the data will be provided. 1/22/2019: the format of the diversion routes will be shape files storedin ArcGIS.
8 | SharePoint backup and restore capability unknown | 2018-05-17 | Clay Packard | 1 | 3 | 3 | L | L |  |  |  | ü |  |  |  |  | Clay to ensure OIT is backing up SharePoint site including document library and OneNote Notebook regularly and reheard a recoery operation | FDOT | Weekly | Closed | [5 empty] | we both need to continue to attach documents via email. | Deliverables shadow copied at SwRI and in FDOT email system.
9 | ITSIQA data based on All Roads Base Map will not be available in time for development and testing of Iteration 1. This affects the all layers of the architecture including drivers, pipelines, data stores, data services, business services and user interface. | 2018-08-05 | Robert Heller | 1 | 4 | 4 | L | L | ü | [7 empty] | Instead of ingestion ITSIQA data as a real time data source during iteration 1, suggest we replace it with SunGuide DMS status and messages for processing. | SwRI | Weekly | Closed | 2018-08-31 |  |  |  |  | This substition needs approval of the FDOT. Decision accepted by FDOT.
10 | The “map backdrop” source has not been identified. There are two possible sources for the backdrop but a final decision has not been made. | 2018-08-29 | Clay Weston | 1 | 4 | 4 | L | H | ü | [8 empty] | FDOT | Monthly | Closed | 2018-07-11 |  |  | #8 |  | Suggest R-ICMS make use of same map backdrop data as used by SunGuide (currently Navteq). SunGuide generates backdrop and roadway network from same data source. We intend to generate backdrop and roadway from AllRoads (assumiing that backdrop is present). If it is not present then we can reopen this risk.
11 | The data sources for SOT are needed for Iteration 2 DFE development and Iteration 3 SOT development. 12/4/2018: This risk applies not only to SOT data but to data needed for R-ICMS in general. See Comments. | 2018-08-29 | Clay Weston | 4 | 4 | 16 | H | L | ü | [8 empty] | FDOT | Weekly | Closed | 2019-04-04 |  |  |  |  | The SOT data was identified in the table as being available from several different sources and the table identified much of the data as being available by dates that are now in the past. Most recently, the source for much of this data has been identified as a future release of ITSIQA. The ICDs (sources, protocols, formats) need to be available for Iteration 2 design, the actual data sources need to be available prior to iteration 2 development. If the data is going to become available from different sources, then there must be some method identified to match data across data sources. E.g. it must be possible to match intersections across different data sources, RCI might have one naming convention and ICM might have another but if you cannot match the intersections from RCI to those in ICM then one of the sources is unuseable. Clay 11/15> Data sources are on track for Iteration 2, and, a intersection identification schema that will work across data sources has been determined 12/4/2018: Data sources are not on track for Iteration 2. SwRI lacks ICDs for Signal Iventory App and SunGuide parking, traffic signal data. SwRI lacks live data sources for ITSIQA (traffic conditions), Ramp Meter, CV, Parking, ATSPM, ITSIQA (TMC), Signal Inventory App, and SunGuide Signal Data (TMDD). | Specific data sources identified in risks below.
12 | Data coverage. The effort to identify data sources has identified sources for different types of data in different jurisdictions. In order to develop / test the SOT tool (and later PRE), there must be a single jurisdiction that has all data sources present. | 2018-08-29 | Angela Bos | 2 | 4 | 8 | M | L |  |  |  | ü | [5 empty] | FDOT | Weekly | Closed | [5 empty] | The current spreadsheet tracks availability of data source, but not the jurisdiction from which the data is available. The spreadsheet almost needs to be expanded to list what in what region data is available. Clay 11/15> Based on Gridsmart being the only TMC and SPM data source we can use initially, should we identify a region based on Gridsmart devices for which we strive to make data available from all other sources § List of Gridsmart intersection in the Data Sources folder: https://fldot.sharepoint.com/sites/FDOT-EXT-TEO/D5TSMO/DataInitiatives/ICMS/Shared%20Documents/10%20Data%20Sources/IMC%20intersections.xlsx?d=w00dc2d598cb04ade92f34d2755f42d47 § Need a list from Table 7 of what's needed for a base test scenario § Need to identify spatial extent of a base test scenario § Need to identify availability of this list for a set of intersections that will work for a base test scenario. Robert will ask Angela to perform this analysis Clay 2019.01.14> § Gridsmart devices (providing TMCs via ITSIQA) are in Maitland and City of Orlando § SwRI will verify they have the signal database for Gridsmart intersections; else, will ask for them from Jay § We have asked the Intersection Inventory Team to collect data for these 32 intersections first □ SwRI will continue participating in design review; next meeting today 1/14 □ Data collection from Gridsmart intersections has been informally provided ® Pre-App data collection chartered by Jeremy for Gridsmart intersections & provided to SwRI on 12/13 for review ◊ Draft excel spreadsheet of collected data ◊ Turn bay length missing ® 32 intersections - need to get schedule for data collection at design review meeting today § We plan to use UCF model for validation of data handling first for initial development § Trafficware has provided a cost estimate with □ Phase 1 completed by May 15, 2019; □ Phase 2 completed by 12/31/2019 □ pending FDOT execution Intellight has committed to providing a non-TMDD interface to the entire ATMS database, and I'm still working with them for a TMDD conversion interface, alternatively, FDOT may have their own TMDD conversion interface developed for Intellight.
13 | SunRail GTFS-RT data service interruption | 2018-09-06 | Claudia Paskauskas | 4 | 1 | 4 | L | H | ü | ü | [6 empty] | Quarterly review for schedule impacts until the service interruption is resolved | FDOT | Quarterly | Closed | 2021-04-01
14 | ITSIQA Traffic Data Feed is not stable for Iteration 2 ingestion | 2019-04-04 | Robert Heller | 2 | 4 | 8 | M | L | ü | ü | [5 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | We have experienced multiple occassions when we attempted to access the ITSIQA feed and find issues. This cycle costs us develper time and money. To date we have not asked for additional funds, but we need feed to be finalized. The issue as of 4/4 is that the All-Data and No-HERE data feeds are nearly identical which seems unusual.
15 | ITSIQA Turning Movement Counts data feed is not stable for Iteration 2 ingestion | 2019-04-04 | Robert Heller | 3 | 2 | 6 | M | L | ü | ü | [5 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | Latest iteration of ITSIQA feed showed only through counts. When we ask ITSIQA about this we are usually told that the correction is out of scope. Can you define exactly what will be in the feed, when it will be in the feed and the process for filing issues. |  | ü
16 | SunGuide CCTV Live Streams / DIVAS ICD availability for iteration 2 | 2019-04-04 | Robert Heller | 4 | 2 | 8 | M | M | ü | [6 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | If this is not available, then the fall back is to use the old feed temporarily and then use the new feed when available. This means doing the interface twice.
17 | Intersection Geometry (IIA) will not have data needed by SOT and Aimsun Simulation Software for iteration 3 | 2019-04-04 | Robert Heller | 4 | 4 | 16 | H | L | ü | ü | [5 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | Comments against the IIA SDD have been slow in response or seemingly ignored. We have requested an ICD and not received it. They have missed all target delivery dates for the needed design documentation. Getting the data for use in SOT and AIMSUN is critical.
18 | API for retrieving response plans from ArcGIS is not available to develop of R-ICMS DFE driver for Iteration 2. | 2019-04-04 | Robert Heller | 4 | 4 | 16 | H | L | ü | ü | [5 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | Lack of response plans makes it much more difficult to develop ERE, PRE and EVE. Having the data ingested into R-ICMS in Iteration 2 allows us to develop against the data in Iteration 3. Since it is not available, the schedule is at risk for all Iterations following iteration 2.
19 | The UCF model will not cover intersections for which there is data to develop & test ERE, PRE, EVE and SOT | 2019-04-04 | Robert Heller | 3 | 2 | 6 | M | M | ü | [6 empty] | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | This is largely unknown until somebody looks at the data.
20 | GTFS aggregator format feed is proposed to be JSON instead of GTFS standard CSV. | 2019-04-04 | Robert Heller | 4 | 2 | 8 | M | M | ü | ü | ü |  |  |  |  | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | Paskauskas stated in her SDD comments that this feed would be JSON not the CSV or protobuf of the statndard. This imposes additional costs on development since the CSV feed is complete for GTFS driver.
21 | GTFS aggregator feed will not be available for development during Iteration 3. Feed must be present and stable. | 2019-04-04 | Robert Heller | 4 | 2 | 8 | M | L | ü | ü | ü |  |  |  |  | ü |  | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | Paskauskas has stated that the SOS has not been developed for this aggregator feed. Is there a schedule for its development? 5/21/2020: No additional information has been provided for GTFS RT. There are no ICDs or live data available at this time
22 | SunGuide 8.0 changes will introduce changes that will require changes within the R-ICMS | 2020-12-01 | Clay Weston | 4 | 4 | 16 | H | L | ü | ü | ü |  |  |  |  | ü | Through contract modification, time will be spent to allow time/budget to modify and test the R-ICMS to ensure it works properly with SunGuide 8.0 | FDOT | Monthly | Closed | 2021-04-01 |  |  |  |  | The system was modified to support SunGuide 8.0 and is now working propoerly in coordination.
23 | Shared GIS resources could cause lag in production website | 2020-12-01 | Clay Weston | 2 | 3 | 6 | M | M |  |  |  | ü |  |  |  |  | Currently EPIC, FDOT, ESRI are working towards retooling the GIS enviornment to be more efficient and streamlined. | FDOT | Monthly | Increasing | [5 empty] | This risk is currently occurring. Currently FDOT, SwRI, and EPIC are working to address this by standing up another GeoEvent server that will not be shared. This should help mitigate the slow downs and failures we are seeing on the current system. Additionally, more resources are being provided to the server to help.
24 | MongoDB system failures | 2021-04-01 | Clay Weston | 3 | 3 | 9 | H | L |  |  |  | ü |  |  |  |  | EPIC and SwRI are currently working with MongoDB support and FDOT IT to help address these issues. We are constantly monitoring the servers and proactively restarting processes when it seems slow downs may occur | SwRI | Monthly | Increasing
25 | Aimsun V/C and score results | 2021-06-04 | Clay Weston | 2 | 2 | 4 | L | H |  |  |  | ü |  |  |  |  | Aimsun sometimes reports seemingly invalid V/C values causing response plans to not be considered. | Aimsun | Monthly | New | [5 empty] | Aimsun is currently looking into why this is happening and suspects that it is based on the underlying model that Cambridge put together.
26 | [5 empty] | 0
27 | [5 empty] | 0
28 | [5 empty] | 0
29 | [5 empty] | 0
30 | [5 empty] | 0
31 | [5 empty] | 0
32 | [5 empty] | 0
33 | [5 empty] | 0
34 | [5 empty] | 0
35 | [5 empty] | 0
36 | [5 empty] | 0
37 | [5 empty] | 0
38 | [5 empty] | 0
39 | [5 empty] | 0
40 | [5 empty] | 0
42 | [5 empty] | 0
43 | [5 empty] | 0
44 | [5 empty] | 0
45 | [5 empty] | 0
46 | [5 empty] | 0
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
iVDS goes away in June to be replaced by DIVAS. Needed for video for GUI when camera icon is clicked Clay 1/29/2019> Discussed with Clint Smith (the new Russell Allen, the PM of DIVAS). It is earlier in the process than documentation has been developed. Let's check back in April 2019 This was discussed on 4/8> We may be able to get the CCTV's remote URL from databus's CCTV stream that's already being ingested, and open that URL from the HTML5 browser directly. To be investigated.
Clay to book a meeting with Mongo, Claudia, and Jeremy and/or Tushar to discuss a more favorable pricing model than linear.
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | 2019-06-04 | Email |  | Heller | Patel / Dilmore | No
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | 2019-06-14 | Email |  | Heller | Patel / Packard | No
Note on J7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q7: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q8: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q9: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q10: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q11: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q12: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q13: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q14: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q15: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q16: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q17: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q18: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q19: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q20: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q21: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q22: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q23: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q24: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q25: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q26: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q27: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q28: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q29: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q30: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q31: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q32: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q33: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q34: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q35: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q36: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q37: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q38: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q39: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q40: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q41: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q42: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q43: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q44: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q45: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q46: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q47: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q48: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q49: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q50: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on J51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on K51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on L51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on M51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on N51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on O51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on P51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark
Note on Q51: Heller, Robert W., Ph.D.: Use ALT0252 on the numberic keybad for the tick mark

## Action Item Log
Action Item Log
Project |  | Regional Integrated Corridor Management System |  |  |  |  | Project # | BE521
Project Manager |  | Tushar Patel |  |  |  |  | Sponsor | FDOT District 5 Traffic Operations
R&C Category |  | 2 |  |  |  |  | Worksheet Updated | 2019-07-01
ID | Action Item | Owner | Priority | Completed | Source | Date Assigned | Planned Completion | Actual Completion | Risk Log # | Issues Log # | Decision Log # | Change Control Log # | Comments / Status Notes
|  |  | H / M / L | Options are: New Open Pending Completed | Mgt Team Stakeholder etc. | "Date Assigned" | "Planned Completion" | "Actual Completion" | Risk Log # | Issue Log # | Decision Log # | Change Control Log #
1 | SwRI to provide needed date, quantities, for production systems (hardware and software) during Preliminary Design. | Robert Heller | M | OBE | Mgt | 2018-04-03 | 2018-07-31 | [5 empty] | Superceeded by AI #53. Action Item created during the Project Kickoff meeting from Tushar Patel. FDOT needs this system list to accommodate the FDOT procurement cycle lead time. This is being pushed out to CDR I.
2 | SwRI to provide SQL Server sizing estimates for data and processor | Robert Heller | M | OBE | Mgt | 2018-04-03 | 2018-07-31 | [5 empty] | Superceeded by AI #53. This is needed to make sure there is sufficient space on the DEPARTMENT servers for the ICMS, and so FDOT can procure needed resources.
3 | SwRI to provide list of Microsoft user accounts for FDOT Project SharePoint site access. | Robert Heller | M | Completed | Mgt | 2018-04-03 | 2018-04-06 | 2018-04-05
4 | Paskauskas will use the Table 7 from Technical Requirements to identify data sources and data formats. | Claudia Paskauskas | M | Completed | Team | 2018-04-03 | [6 empty] | This needs to be split into one for each iteration. SwRI needs to identify what data sources are to be in each iteration and then put dates on information need date. All complete - any exceptions are deferred to separate individual broken out AI's
5 | SwRI will work with Demetrius Lewis to complete and submit access report forms for access to the data sources identified by InNovo | Robert Heller | L | Completed | Team | 2018-04-03 | [6 empty] | Weston form submitted 5/30/18. More in progress. VPN tunnel meeting on 5/31. System account forms submitted 7/10.
6 | SwRI and Kapsch to have side meeting during requirements walkthrough to discuss formats for rules, response plans. Matt to provide discussion notes and data format information on these items. | David V. | M | Completed | Team | 2018-04-03 | [6 empty] | Meeting held -2018.06.12 - Response Plans & Rules (see notes in OneNote) Robert will ask David V. if he has a preferred rules format, or if we need to have another meeting
7 | Review and comment or approve the PSEMP template | Clay Packard | H | Completed | Mgt | 2018-04-03 | 2018-04-06 | 2018-04-06
8 | Clay W. and Claudia to coordinate data sources, number of instances there will be, and maintain a status of data sources prioritized needs and status, and filters (for API access) associated with each data source. | Claudia Paskauskas | H | Completed | Team | 2018-04-24 | [6 empty] | Identified during Requirements Walkthrough
9 | Clay W. and Clay to coordinate live ITSIQA data access. | Clay P. | H | Completed | Team | 2018-04-24 | 2018-12-31 | 2019-01-02 |  |  |  |  | Identified during Requirements Walkthrough. As of 5/31 this was complete, but ITSIQA needs revision. ICD was delivered 10/31, deployment/available scheduled for 12/31 Clay P. 1/10/2019> Updated system available 12/30 (announcement sent 1/2/2019). Action item assigned to Clay W. for verification
10 | Clay W. and Steve J. to coordinate VPN access | Clay Weston | M | Completed | Team | 2018-04-24 | [6 empty] | Identified during Requirements Walkthrough. 5/31 is underway. | Monthly
11 | FDOT to facilitate how 3 SunGuide software systems (D5, CFX, FTE) will work together (get with Derek, Tucker, CFX folks FTE folks) | Jeremy Dilmore | L | Completed | Team | 2018-04-24 |  | 2018-07-11 |  |  |  |  | Identified during Requirements Walkthrough. Wait for FDOT CO to finish investigation of per user. Need to be careful to ensure RCA is the correct solution and works correctly for the User Needs of R-ICMS D5 will ensure R-ICMS is included in user needs when CO implements RCA in SunGuide |  | The current spreadsheet tracks availability of data source, but not the jurisdiction from which the data is available. The spreadsheet almost needs to be expanded to list what in what region data is available. Clay 11/15> Based on Gridsmart being the only TMC and SPM data source we can use initially, should we identify a region based on Gridsmart devices for which we strive to make data available from all other sources § List of Gridsmart intersection in the Data Sources folder: https://fldot.sharepoint.com/sites/FDOT-EXT-TEO/D5TSMO/DataInitiatives/ICMS/Shared%20Documents/10%20Data%20Sources/IMC%20intersections.xlsx?d=w00dc2d598cb04ade92f34d2755f42d47 § Need a list from Table 7 of what's needed for a base test scenario § Need to identify spatial extent of a base test scenario § Need to identify availability of this list for a set of intersections that will work for a base test scenario. Robert will ask Angela to perform this analysis Clay 2019.01.14> § Gridsmart devices (providing TMCs via ITSIQA) are in Maitland and City of Orlando § SwRI will verify they have the signal database for Gridsmart intersections; else, will ask for them from Jay § We have asked the Intersection Inventory Team to collect data for these 32 intersections first □ SwRI will continue participating in design review; next meeting today 1/14 □ Data collection from Gridsmart intersections has been informally provided ® Pre-App data collection chartered by Jeremy for Gridsmart intersections & provided to SwRI on 12/13 for review ◊ Draft excel spreadsheet of collected data ◊ Turn bay length missing ® 32 intersections - need to get schedule for data collection at design review meeting today § We plan to use UCF model for validation of data handling first for initial development § Trafficware has provided a cost estimate with □ Phase 1 completed by May 15, 2019; □ Phase 2 completed by 12/31/2019 □ pending FDOT execution Intellight has committed to providing a non-TMDD interface to the entire ATMS database, and I'm still working with them for a TMDD conversion interface, alternatively, FDOT may have their own TMDD conversion interface developed for Intellight.
12 | SwRI to review the Scope of Services to identify requirements stated but not in Exhibit C Requirements list. | SwRI | M | Completed | Team | 2018-04-24 |  | 2018-05-18 |  |  |  |  | Identified during Requirements Walkthrough
13 | NTP required for Task 6 - Training | FDOT | L | Completed | See Comments | 2018-05-02 | 2020-01-01 | 2021-01-01 |  |  |  |  | Original NTP was for Tasks 1, 2, 4 and 5.
14 | NTP required for Task 7 - OM&S | FDOT | L | Completed | See Comments | 2018-05-02 | 2020-03-12 | 2021-01-01 |  |  |  |  | Original NTP was for Tasks 1, 2, 4 and 5.
15 | Clay to email Justin Sorg | Clay Packard | M | Completed |  | 2018-05-17 | 2018-05-17 |  | 8
16 | Tawny to provide Osceola County facilities | FDOT | L | Completed | Mgt | 2018-05-17
17 | Clay W. to follow-up with Demetrius and Steve for site-to-site VPN and user credentials | FDOT | H | Completed | Mgt | 2018-05-17
18 | Clay W. to submit SARs for himself and other users to be using the D5 network | FDOT | H | Completed | Mgt | 2018-05-17 | 2018-06-15 | [5 empty] | Weston SAR has been submitted.
19 | Review Issues Log Items related to requirements and scope after PDR | SwRI | M | Completed | Mgt |  | 2018-07-31 | 2018-10-01 | [7 empty] | This is largely unknown until somebody looks at the data.
20 | Closeout SOT requirements (comment resolutions, etc.) | SwRI | M | Completed | Mgt |  | 2018-07-13 | 2018-10-01 |  |  |  |  | Updated SOT reqruiements provided to FDOT on August 27.
21 | Clay P to provide Intersection Signal ATMS interface analysis for traffic signal controller inventory (timing plans, etc.), status, and control (not turning count data) | FDOT | M | Completed | Mgt | 2018-06-11 |  | 2018-11-16 |  |  |  |  | Clay P. 1/10/2019> Interface analysis completed and sent to vendors as final requirements.
22 | Clay W. to propose Active Directory integration and corresponding req't changes at CDR | SwRI | L | Completed | See Comments | 2018-06-13 | 2018-07-31 | [5 empty] | see notes from Active Directory Integration Call on 2018.06.13 (Web view) in OneNote
23 | Clay W. to propose specific Active Directory integration components (COTS library, custom code following A/D protocol, etc.) to Steve Johnson for his review | SwRI | L | Completed | Stakeholder | 2018-06-26 | 2018-07-31
24 | PDR Comments into PD doc | Clay P. | L | Completed | Team | 2018-06-26 | [6 empty] | Clay P. to incorporate into comments of Draft design - Security - upon token approaching expiration, system will verify user exists and is active prior to issuing new token. Also, if a token is requesting to be replaced with another token having additional permissions, the new token should not start with a fresh timer, but only have the remaining time of the original token.
25 | Operations questions | Clay P. | L | Completed | Team | 2018-06-26 | 2018-07-11 | [5 empty] | Replaced with 25 a - d so they can be tracked separately.
25a | What SunGuide event activity occurs to indicate normal flow, and how is this done in operations, and when is the ICMS event is over. | Clay P. | L | Completed | Team | 2018-06-26 | 2018-07-11
25b | Do we need to operate ICMS events after all SunGuide events have been closed? | Clay P. | L | Completed | Team | 2018-06-26 | 2018-07-11
25c | Can we activate without all agencies? If critical intersections included? Other approval/activation constraints that need to be enforced by R-ICMS. | Clay P. | L | Completed | Team | 2018-06-26 | 2018-07-11
25d | What to do with informational alerts | Clay P. | L | Completed | Team | 2018-06-26 | 2018-07-11
26 | CDR to include full enumeration of unhappy cases for sequence diagrams | SwRI | M | Completed | Team | 2018-06-26 | 2018-07-31
27 | HCS Licensing | Clay P. | M | Completed | Team | 2018-06-26 | 2018-07-31 | [5 empty] | Clay P. to coordinate meeting with Central Office to hash out licensing particulars for R-ICMS development and operation - prior to PDR
28 | Jay to provide sample corridor data (small intersection set of 3 or so) | Jay W. | M | Completed | Team | 2018-06-26 | 2018-06-26 | 2018-06-26
29 | David Vickers to coordinate the validation with HCS / Angela trying to model some of the outlier intersection configurations | SwRI | M | Completed | Team | 2018-06-26 | 2018-07-31 | [5 empty] | Angela has taken this over and is actively being worked from input from Manny.
30 | SOT Workshop Document Review | SwRI | M | Completed | Team | 2018-06-26 |  | 2018-07-05 |  |  |  |  | David Vickers to evaluate the SOT workshop document by the end of next week; include a proposed approach for the evaluation and rules or ask questions. Possibly include a configurable parameter: https://fldot.sharepoint.com/sites/FDOT-EXT-TEO/D5TSMO/DataInitiatives/ICMS/Shared%20Documents/02%20Meetings/SOT%20Workshop/Signal%20Retiming%20and%20SOT%20Workflow.docx?d=w6098a76557384d5dad70391dd1248ba2
31 | CDR to including a table for how info should be displayed to users: Info Feed, email, layer, alert - for each data type/source/more granular bit of info to be communicated to users | SwRI | M | Completed | Team | 2018-06-26 | 2018-07-31 | [5 empty] | David Vickers aggreed to having a proposed table (or more complicated model) for how infromation should be displayed at the apporpriate CDR
32 | Crystal Reports alternatives | Clay P. | L | Completed | Team | 2018-06-26 |  | 2018-07-05 |  |  |  |  | Clay P. Sooner than later would be an outstanding time for us to propose something in addition to Crystal Reports for consideration. Consider this with the filtering and indexing. ○ The department is going to Tableau as a standard Other alternatives are Jasper, QLIK, and many more
33 | Algorithm benefit, thresholds | Matt | M | Completed | Team | 2018-06-26 | 2018-07-01 | 2018-07-09 |  |  |  |  | Matt: Give set of stuff that goes into the algorithm that calculates the benefit for algorithms: Scoring response plans, and scoring signal timing plan sets. Also need thresholds when to discard this. Will make a sample one targeting July 1. Meeting on 7/9 to go over Matt's preliminary information. Action item closed until SwRI requests additional information. Clay suggests having a call to catch up after vendor is selected. David said we will let you know if that is needed at that time.
34 | Token and Role Manager Link | Clay P. | L | Completed | Team | 2018-06-26 | 2018-06-26 | 2018-07-05 |  |  |  |  | Clay P to update the TRM link for the DFE Sandbox: DFE Sandbox - today http://tsmo4planning.cflsmartroads.com/trmanager
41 | Clay P to provide ITSIQA interface changes expected | Clay P. | M | Completed | Team | 2018-06-26 |  | 2018-07-05
42 | Clay P to make a diagram of how each map product, i.e. the All Roads Basemap & Roadway Characteristics Inventory (RCI) is related to one another. | Clay P. | M | Completed | Team | 2018-06-26 |  | 2018-07-11
43 | Clay P. to coordinate Data Sources and their corresponding Data Stores, and will invite a stakeholder consortium to help elicit needs. Jeremy will provide additional detail. | Clay P. | M | Completed | Team | 2018-06-26 |  | 2018-07-10
44 | Clay P. to provide updated ITSIQA ICD with expected changes | Clay P. | H | Completed | Team | 2018-07-11 | 2018-07-13 | 2018-08-31
45 | SwRI to provide rationale for decisions in selection of tool chain, not just results. Heller suggests using the SwRI Decision, Analysis, Resolution (DAR) template which is part of the SwRI CMMI process. First DAR is to address "Parcel vs Package" decision by EPIC. | SwRI | M | Completed | Stakeholder | 2018-07-31 | 2018-11-30 | 2020-01-01 |  |  |  |  | Dilmore requested the development team provide rationale for decisions made in selection of development tools so that rationale can be provided to other organizations within FDOT addressing the same tool selection issues. Will be tied together with the hardware recommendation
46 | Clay to coordinate signal inventory application availability. Need interface specification by 12/31/2018. | Clay P. | H | Completed | Team | 2018-08-23 | 2018-08-30 | 2018-12-31 |  |  |  |  | pending intersection ID scope 1/29>3 ITB's (for procurment with signal vendors) are almost out the door! Design for SII expected soon, no specific date
47 | Clay to coordinate TMC data source (ITSIQA possibly?) | Clay P. | H | Completed | Team | 2018-08-23 | 2018-08-30 | 2018-08-30 |  |  | 10, 11
48 | Clay P. to ask about consolidated, consistent shape file set full attribute set for all school zones. | Clay P. | M | Completed | Team | 2018-08-23 | 2018-08-30 | [5 empty] | Clay P. emailed Chad Lingenfelter on 9/13/2018. Until a response is received, we will us the first page of the PDF to provide school zones on state roads only since we do not have actual location starting and ending points for school zones on non-state roads. Closing item with decision to use avialabile data and additional data can be added later as part of system maintenance.
49 | Clay will coordinate the potential use of SunGuide's map generator tool to build vector map images | Clay P. | H | Completed | Team | 2018-08-23 | 2018-08-30 | 2018-08-30 |  |  |  |  | SunGuide generates raster images, not vector images.
50 | Suresh will investigate if ESRI map can be cached (not dependent on the internet) and able to meet the project's needs. | Epic | H | Completed | Team | 2018-08-23 | 2018-08-30 | [5 empty] | I think this is closed possibly if it has been decided to use SunGuide style map tile generation. EPIC has confirmed the tiles can be cached.
51 | Clay to get definiative/authoritative list of all intersections | Claudia Paskauskas | H | Completed | Team | 2018-08-23 | 2018-08-30 | [5 empty] | See AI 38 - this is covered by the invendory app/API to be provided -
52 | Mapping between GIS and Model | Clay P. or Matt J. | H | Completed | Team | 2018-08-23 | 2018-08-30 | 2018-12-31 |  |  |  |  | To be scoped. May not be necessary. The online model vendor will have to obtain information from R-ICMS APIs, and R-ICMS will need to obtain and interpret results from the online model API. 12/4/2018: What data needs to be mapped? Whose responsibility is this?
53 | Verify Oct 22 deadline can be met for all SOT data source or evaluate project schedule impact | Clay P. | H | Completed | Team | 2018-08-23 | 2018-08-30 | 2018-12-31 | 11 |  |  |  | Waiting on plans for data collection efforts in order to evaluate R-ICMS schedule impact. See AI# 38 (Intersection Invendory), 48 (ITSIQA SPM availability), Robert will talk to Angela for SOT impact
54 | Question whether it is desired to have notification by data type and time ranges be configurable per user? Example, for weather alerts, should users be able to turn these off? Requirements don't cover this functionality. | Angela Bos | M | Completed | Team | 2018-06-22 | 2018-08-30 | 2018-08-30 |  |  | 7
55 | Clay to provide sample ATSPM .dat and .csv files | Clay P. | M | Completed | Team | 2018-09-06 | 2018-09-07 | 2018-10-11
56 | Clay to coordinate ATSPM architecture questions: | Clay P. | H | Completed | Team | 2018-09-06 | 2018-09-12 | 2018-10-11 |  |  |  |  | How does ITISQA get ATSPM data, is Elastic able to serve real-time data or is an alternative engine such as Mongo be more suitable, How will ATSPM website be operated/maintained (outside R-ICMS scope), should FDOT perform ETL of ATSPM and provide to R-ICMS as data source rather than transferring ETL to R-ICMS architecture discussed and migration plan extended. We will still use Elastic initially for the Sandbox, but will include now the plan for future migration to Kafka/Mongo as provided by SwRI.
57 | Clay W. to propose architecture for obtaining arrival on green and other potentially needed derived SPMs originally available from ATSPM | Clay P. | M | Completed | Mgt | 2018-09-17 | 2018-12-17 | [5 empty] | Discuss on Thursday, 9/20; Clay P.> discussing with John Hope on 10/2 at 1:30 pm Need availability date
58 | Ensure signal/controller IDs in the signal inventory app are mappable to ITSIQA (IMC, MV, ATSPM), TMDD | Clay P. | H | Completed | Team | 2018-09-26 | [6 empty] | Already discussed with Intersection Inventory App team for multiple IDs. will discuss with John Hope on 10/2 at 1:30 pm clay proposed controller ID schema that was well received; Angela reviewing for scenario of multiple intersections having same controller.
59 | Ensure signal/controller IDs in the signal inventory app are mappable to modeling engine | Clay P. | H | Completed | Team | 2018-09-26 | [6 empty] | RICMS needs to send suggested timing plans for signals to the ME in order to evaluate response plans and SOT results. This is an unassigned task. I believe it will be assigned to the modelling consultant (Cambridge) after the modelling product is on board
60 | Define format and structure of data for bulk loaded response plans | SwRI & Kapsch | M | Completed | Team | 2018-09-26 | [6 empty] | For iteration 2; Meeting on Thursday to discuss; continuing Monday 11/19; 12/4/2018: Response plans will be entered into the system using ArcGIS. There will be no bulk loading of response plans except for the ICMS retrieve from ArcGIS.
61 | RICMS requirements R126 (allocated to iteration 2) states that we will support Single Sign On, but Directory Server Authentication (DSA) may be more feasible in the context of a web application. This should be further investigated to detemine if a CR to change requirements is necessary. | SwRI | M | Completed | Team | 2018-10-08 | 2019-03-31 | [5 empty] | For iteration 2
62 | Robert to provide hardware and software configuration, quantities, and needed by dates | SwRI | M | Completed | Mgt | 2018-11-16 | 2018-11-30 | 2019-01-22 |  |  |  |  | to be initially discussed 11/16 Clay 1/10> Robert provided 90% draft with questions for FDOT.
63 | Clay P. to research past ivedds correspondence and suggest how to get Internet routable / public facing camera feeds. | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-28 |  |  |  |  | emails collected, provided, and stored here OneNote --> Data Sources --> D5 Video for R-ICMS (near the bottom)
64 | Clay P. to research requirements for providing API access to historic static data. | Clay P. | M | Completed | CDR-2 | 2019-01-22 | 2019-01-29 | [5 empty] | Clay P. to confirm all data required for retention to be accessible via API. related action item - Claudia to provide retention requirements. Clay 2019.01.29> Please provide API access for transformed data for 3 years for all data sources - static or dynamic; ok to de-dup, ok to transform
65 | Clay P. to review and discuss with Jeremy the requirement to store ITSIQA feed without HERE.com data. ITSIQA has 2 output streams; one configured to not use HERE.com data. This will double the amount of resources needed to store ITSIQA data. | Clay P. | M | Completed | CDR-2 | 2019-01-22 | 2019-01-29 | 2019-01-29 |  |  |  |  | This is needed
66 | Clay P. to discuss with John Hope for a smaller dataset output when HERE.com is not used to reduce the annual storage rate. | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-28 |  |  |  |  | John hope confirmed that output
67 | Clay P. to check with John Hope and Claudia to discuss future ARBM links as Claudia is coordinate additional HERE.com data availability. | Clay P. | M | Completed | CDR-2 | 2019-01-22 | [6 empty] | Email sent to Mark D. from Central Office on status of 2018 ARBM. D5 is on the same page; Clay to work with Jay. Clay 2019.01.29> No longer a Project pending item - it's decided. Clay, outside of this project, will champion this to all other projects. Jay has verbally agreed and will work with Manny.
68 | Clay P. and Claudia to discuss link ID vs. TMC for future HERE.com data. See Comments. Need to review roads for making the request to add to TMCs. Keith Smith will support. | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-02-26 |  |  |  |  | Clay 1/29/2019> Some roads do not yet have TMC codes, HERE.com does have raw probe data for these roads, but use linkID's, which maps nicely to the All Roads Basemap & the HERE streets maps. Here.com offered FDOT a 2-phased approach: Phase 1: us to identify roads and they will include the probe data based on linkid segmentation will be part of the current feed. They think they already provide it but we don't get it because we look for TMCs and ignore other - but they will make sure this is included. Phase 2: HERE.com will present list of roads we selected to the TMC board, and ask them to be added so we can get them included with TMC codes. 2/26/2019> Keith validated this issue of missing TMCs for road segments was minimal. Claudia will work torwards getting complete routes; however, there's plenty of coverage to use TMCs as originally planned. Please let us know if there is anything missing that is needed for the rpoject so we can immediately request that it is added - it takes HERE.com a quarter plus our integration time, and we can probably have John add something temporary in ITSIQA much faster (similar to geting SR 426 online)- just let us know what you discover is needed.
69 | Clay P. to check if iVEDDS properly blocks blocked video when blocked by SunGuide operator | Clay P. | M | OBE | CDR-2 | 2019-01-22 | [6 empty] | email sent to D5 group on 1/28. iVDS is going away - we will be using DIVAS when it is available. It is under development so this will be on hold. This is a non-issue - whatever DIVAS will provide we are comfortable providing to users of R-ICMS.
70 | Clay W. to upload the updated data sources list | Clay W. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-28
71 | Claudia to add a column to the data sources list to indicate retention period | Claudia | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-29 |  |  |  |  | 3 years for all data sources
72 | Claudia to discuss cold storage policy, and if transformed data needs to be stored in cold storage. | Claudia | M | Completed | CDR-2 | 2019-01-22 | [6 empty] | After discussion - 3 years required retention for all data, needs API retrieval of transformed data.
73 | Clay and Claudia to discuss with Jeremy and Tushar if its ok to purge duplicate raw data records, e.g. DMS status update messages. | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-29 |  |  |  |  | Ok to purge / de-dup records containing purely redundant data
74 | Robert will propose a solution to the use case of pulling data for a time period and ensuring a status for the beginning of the window (Robert's notes #3). | Robert | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-22
75 | Steve to provide Clay W with password requirements | Steve | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-22 |  |  |  |  | sent via email
76 | Robert to write up the request to accept shared rights to SwRI developed software used for R-ICMS to Tushar and Jeremy | Robert | M | Completed | CDR-2 | 2019-01-22 |  | 2019-02-06 |  |  |  |  | SwRI will provide all IP to FDOT.
77 | Clay W. to add to the rules: look at device online, offline, and auto-reject with 0s timeout. | Clay W. | M | Completed | CDR-2 | 2019-01-22
78 | SwRI to add Description field to approval profiles to aid in the enabling and disabling | Clay W. | M | Completed | CDR-2 | 2019-01-22
79 | SwRI to look at a couple of design requests | SwRI | M | Completed | CDR-2 | 2019-01-22 |  | 2020-06-01 |  |  |  |  | • Clay P requests a view to allow an R-ICMS administrator to view a list of ICMS users (i.e. ones within the ICMS group of A/D), then when the administrator clicks on a user, the view will show an analysis of their security roles, permissions, and device groups, and which ones they do and do not have access to. • Robert requests an admin function to email a request to FDOT to add a set of roles to a user.
80 | Yi to provide table of signals, and folder structure | Yi | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-22 |  |  |  |  | sent via email and stored in OneNote-->DataSources-->ATSPM-->bottom page
81 | Tushar will look at costs and funding and state discounts for h/w | Tushar | M | Completed | CDR-2 | 2019-01-22
82 | Robert will look at adjusting the processor to disk space ratio to see if we can reduce the cost | SwRI | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
83 | Robert will look at Windows desktop rather than server | SwRI | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
84 | Robert will look at alternative storage/compute approaches | SwRI | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
85 | Sutha will confirm that ArcGIS Desktop v10.6 - with a quantity of 1 Concurrent User Licensing will be sufficient for O&M | Sutha | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
86 | Sutha will provide hardware configuration required for single server & high availability option. | Sutha | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
87 | Tim (Kapsch) will confirm that ESRI ArcGIS Enterprise Server and Desktop concurrent license will meet the needs of Diversion Route O&M. | Tim | M | Completed | CDR-2 | 2019-01-22 | 2019-02-19
88 | Clay to send out the TMDD requirements to Angela | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-22 |  |  |  |  | email sent; also located in OneNote --> Signal Optimization section --> TMDD requirements page
89 | Claudia to get schedule for the Transit Aggregator | Claudia | H | Completed | CDR-2 | 2019-01-22 |  | 2020-04-01 |  |  |  |  | Clay 1/29/2019> This is not yet developed and will be on hold until after the intersection inventory; let's check back in March 2019.
90 | Clay to send the current DRAFT diversion routes to SwRI for their early review | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-22 |  |  |  |  | see SHarePoint doc library --> Design --> Miscellaneous folder
91 | Schedule a GUI mockup review | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-02-11 |  |  |  |  | Scheduled for Feb 19, 2019
92 | Matt to produce (with input from model engine team) a proposed prioritization strategy at the kickoff meeting (mid to late February). | Matt | M | Completed | CDR-2 | 2019-01-22
93 | Clay to review with Steve the permissions-based configuration for announcements and alerts: | Clay P. | M | Completed | CDR-2 | 2019-01-22 |  | 2019-01-29 |  |  |  |  | Clay 2019.01.29> Discussed with Jeremy and Steve. It's ok to use permissions to build a recipient list as a group in some cases; however, there is also a need to send specific users annoucements, alerts, emails, etc. based on something other than role membership, includnig, but not limited to, the user requesting a SOT run or an evaluation and the system prompting them that it has been completed, or, requesting their approval for a response plan item within their specfic jurisdiction. Active Directory contains this information if it is not stored in a cache in the R-ICMS. For example, a user requests an SOT job. the user token is available as an attribute of the job. When the job completes, R-ICMS can use teh user token to get the email address from Active Directory if that user is no longer logged in - in order to notify that specific user that their requested SOT run has completed.
94 | Matt to provide old ICD, we will get a new one after Aimsun is under contract. | Matt | M | Completed | CDR-2 | 2019-01-22 | [6 empty] | sent via email and attached to Modelling section of OneNote
95 | Provide SDD comments to SwRI | Clay P. | H | Completed | Mgt | 2019-01-22 |  | 2019-02-20
96 | Clay to provide DIVAS information to SwRI | Clay P. | H | Completed | Mgt | 2019-01-29 | 2019-04-01 | 2019-04-01 |  |  |  |  | iVDS goes away in June to be replaced by DIVAS. Needed for video for GUI when camera icon is clicked Clay 1/29/2019> Discussed with Clint Smith (the new Russell Allen, the PM of DIVAS). It is earlier in the process than documentation has been developed. Let's check back in April 2019 This was discussed on 4/8> We may be able to get the CCTV's remote URL from databus's CCTV stream that's already being ingested, and open that URL from the HTML5 browser directly. To be investigated.
97 | Contact Mongo | Clay P. | M | Completed | Mgt | 2019-01-29 | [6 empty] | Clay to book a meeting with Mongo, Claudia, and Jeremy and/or Tushar to discuss a more favorable pricing model than linear.
98 | Provide VDD comments to SwRI | Clay P. | H | Completed | Mgt | 2019-02-04 |  | 2019-02-20 |  |  |  |  | Clay P. has embedded comments into document in SharePoint and has sent to Kevin Miller on 2/4
99 | ATSPM copy to folder - execution and permissions to SwRI and enable/disable feature | Clay P. | H | Completed | Mgt | 2019-02-11 | 2019-02-19
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | M | Completed |  | Heller | Patel / Dilmore | 2019-04-01 |  |  |  |  | SwRI invoice was sent and paid.
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | L | Completed |  | Heller | Patel / Packard | 2019-06-06 | 43633
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | L | Completed |  | Heller | Patel / Packard | 2019-06-06 | 43633
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | L | Completed |  | Heller | Patel / Packard | 2019-06-14

## Issues Log
Issues Log
Project |  | Regional Integrated Corridor Management System |  |  | Project # |  |  | BE521
Project Manager |  | Tushar Patel |  |  | Sponsor |  |  | FDOT District 5 Traffic Operations
R&C Category |  | 2 |  |  | Worksheet Updated |  |  | 2019-04-04
ID | Issue Description | Importance: High, Medium, Low | Identified By | Date Opened | Status: New, Open, Pending, Escalated, Closed | Project Impact: How will this impact scope, schedule, cost or quality? | Action Plan/Resolution | Owner | Date Assigned | Planned Resolution Date | Actual Resolution Date | Date Closed | Risk Log # | Issue Log # | Decision Log # | Change Control Log # | Notes
1 | During negotiations for this contract, SwRI was told that the API between the modeling engine and the ICMS software was to be defined by SwRI and the ME would adapt. During the Q&A for the ME contract, they were told ICMS would implement the ME API. | High | Robert Heller | 2018-04-03 | Open | Can result in the two systems (ICM & ME) not exchanging data which will lead to ECR an delay in progress. | SwRI worked in conjunction with Aimsun to collobratively build the interfaces between the simulation engine and the R-ICMS. | FDOT
2 | UI for Modeling Engine (ME) parameters ref ERE 1.22.1.2 | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Interpretation of ERE 1.22.1.2 applies to parameters for the rules engine those of the Modeling Engine. The Modeling Engine will have its own GUI.
3 | Notify impacted agencies | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01
4 | Table 7 implies only a single instance of SunGuide, but discussion considered adding CFX and FTE. | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | single instance of sunguide
5 | PRE 1.20.3.16 captures response plan element types. it is out of place. | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Moved
6 | There are numerous issues relating to SunGuide construction events. How do you extract from a construction event that it has an active lane closure. | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Construction events are events. We will extract lane closures from the events.
7 | User need for DFE system operations - administration and associated status to be collected / reportable / alarmable. Include child requirements. | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | added user need
8 | Non-periodic outages and alerting. What defines an outage | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Added requirements.
9 | UI. Agency approval of response plans | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Added requirements.
10 | UI. Rules parameters in the IEN to match 1.22.1.2 | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | 2019-01-02 | 2018-04-25 | SRS Submittal | 2018-05-18 |  | Identified during Requirements Walkthrough. As of 5/31 this was complete, but ITSIQA needs revision. ICD was delivered 10/31, deployment/available scheduled for 12/31 Clay P. 1/10/2019> Updated system available 12/30 (announcement sent 1/2/2019). Action item assigned to Clay W. for verification |  |  |  | Added requirements.
11 | UI. Ability to display confirmation of action plan execution to ICM manager | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Added requirements. | Monthly
12 | UI. Ability to display EVE results (might be in EVE) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-05-18 | [5 empty] | Added requirements. |  | The current spreadsheet tracks availability of data source, but not the jurisdiction from which the data is available. The spreadsheet almost needs to be expanded to list what in what region data is available. Clay 11/15> Based on Gridsmart being the only TMC and SPM data source we can use initially, should we identify a region based on Gridsmart devices for which we strive to make data available from all other sources § List of Gridsmart intersection in the Data Sources folder: https://fldot.sharepoint.com/sites/FDOT-EXT-TEO/D5TSMO/DataInitiatives/ICMS/Shared%20Documents/10%20Data%20Sources/IMC%20intersections.xlsx?d=w00dc2d598cb04ade92f34d2755f42d47 § Need a list from Table 7 of what's needed for a base test scenario § Need to identify spatial extent of a base test scenario § Need to identify availability of this list for a set of intersections that will work for a base test scenario. Robert will ask Angela to perform this analysis Clay 2019.01.14> § Gridsmart devices (providing TMCs via ITSIQA) are in Maitland and City of Orlando § SwRI will verify they have the signal database for Gridsmart intersections; else, will ask for them from Jay § We have asked the Intersection Inventory Team to collect data for these 32 intersections first □ SwRI will continue participating in design review; next meeting today 1/14 □ Data collection from Gridsmart intersections has been informally provided ® Pre-App data collection chartered by Jeremy for Gridsmart intersections & provided to SwRI on 12/13 for review ◊ Draft excel spreadsheet of collected data ◊ Turn bay length missing ® 32 intersections - need to get schedule for data collection at design review meeting today § We plan to use UCF model for validation of data handling first for initial development § Trafficware has provided a cost estimate with □ Phase 1 completed by May 15, 2019; □ Phase 2 completed by 12/31/2019 □ pending FDOT execution Intellight has committed to providing a non-TMDD interface to the entire ATMS database, and I'm still working with them for a TMDD conversion interface, alternatively, FDOT may have their own TMDD conversion interface developed for Intellight.
13 | Agency user need to interact with the agency. (maybe ask Natalie) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
14 | Bulk loader for rules and response plans | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
15 | GUIs for response plan elements response plans and rules | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
16 | Information feed, and associated derived requirements | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
17 | Permissions - per-agency: digitally sign (PE only), Modify | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
18 | The SOT landing page table will be filterable by default to the configured corridors within the agency of the user | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
19 | History of analysis (SOT) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
20 | Requirement to modify the offsets | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting. |  |  | This is largely unknown until somebody looks at the data.
21 | Requirements to initiate a simulation from the corridor details page (having the offsets) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
22 | Define a corridor; corridor management page | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | 2018-11-16 | 2018-04-25 | SRS Submittal | 2018-10-01 |  | Clay P. 1/10/2019> Interface analysis completed and sent to vendors as final requirements. |  |  |  | TBD SOT User Meeting.
23 | SOT screens should have a revert button to revert to the last saved version | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
24 | Calculate total delay as child to 1.45.2 | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
25 | ICMS Event Owner, and re-assignment of, and permissions (manager needs access to take ownership) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
26 | ICMS Event List should contain a shortcut to filter the list to "My Events" | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
27 | Video (iVEDDS) data source - but not stored | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | This is a scope change.
28 | Agency Profile definition (for changing signals and its devices) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
29 | View the embedded CCTV image in the clicked ICMS event icon provided information 1.1.8 | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | This is a scope change.
30 | Timeframes to clear alarms and alerts | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Deferred to Critical Design.
31 | Inferred requirements in the Scope not already captured in the preliminary requirements | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Complete.
32 | Intersection Plans Recommendation | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
33 | MIMS button - open MIMS in new window/tab without redirecting this screen / loosing the current state of the SOT review/modification in progress | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
34 | Map button - open Map in new window/tab without redirecting this screen / loosing the current state of the SOT review/modification in progress | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | TBD SOT User Meeting.
35 | Cameras button - open Camera in new window or popup without redirecting this screen / loosing the current state of the SOT review/modification in progress | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Scope change (IVEDDS is new data source)
36 | May be others from scope (need scope review) | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Complete.
37 | Sending events to SunGuide, associating SunGuide events to ICMS events; not requiring double data entry between SunGuide events and ICMS events | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
38 | Sending emails while executing response plans | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
39 | Constraint: The ETL shall support a maintenance mode that allows maintenance of the system while continuing to download data from data sources so that there is no data gap caused by the maintenance mode | Medium | Requirements Walkthrough | 2018-04-25 | Closed | Unknown if this is NEW requirement or if it is in the Scope of Services. | Add to SRS; Confirm existing or new. | SwRI | 2018-04-25 | SRS Submittal | 2018-10-01 | [5 empty] | Added requirements.
41 | The contract says something about the department providing an ArcGIS server for use by the project. The ArcGIS server will be loaded with various data provided by FDOT in GIS, Excel, text, Word, etc. file formats. This includes base map daa, school locations, etc. If the destinaion of the data is the ArcGIS server, then does FDOT expect the SwRI DFE team to build APIs to access this data? | Medium | Design Preparation | 2018-07-26 | New | Needs response as we build out the GIS server. | It was determined that GIS will be used to house the response plans and the R-ICMS will query the GIS Rest API in order to retrieve the response plans | [9 empty] | ArcGIS provides APIs to retrieve data. This allows retrieval of data by R-ICMS from ArcGIS. Will the R-ICMS API for this data access ArcGIS as the source? Or will it retrieve the data from an R-ICMS DFE data source?
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
iVDS goes away in June to be replaced by DIVAS. Needed for video for GUI when camera icon is clicked Clay 1/29/2019> Discussed with Clint Smith (the new Russell Allen, the PM of DIVAS). It is earlier in the process than documentation has been developed. Let's check back in April 2019 This was discussed on 4/8> We may be able to get the CCTV's remote URL from databus's CCTV stream that's already being ingested, and open that URL from the HTML5 browser directly. To be investigated.
Clay to book a meeting with Mongo, Claudia, and Jeremy and/or Tushar to discuss a more favorable pricing model than linear.
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | 2019-06-04 | Email |  | Heller | Patel / Dilmore | No
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | 2019-06-14 | Email |  | Heller | Patel / Packard | No

## Decision Log
Decision Log
Project |  | Regional Integrated Corridor Management System |  |  |  |  | Project # |  | BE521
Project Manager |  | Tushar Patel |  |  |  |  | Sponsor |  | FDOT District 5 Traffic Operations
R&C Level |  | 2 |  |  |  |  | Worksheet Updated |  | 2019-04-04
ID | Question / Issue / Action Description | Date Entered | Entered By | Date when Decision Needed | Project Impact (Scope, Schedule, Cost) | Decision Made | Decision-Maker | Date Decision Made | Comments / Notes | Status (New, Open, Pending, Closed, Escalated) | Risk Log # | Issue Log # | Action Item Log # | Change Control Log # | Requirement #(s) | Post-Decision Action To Be Taken | Action Owner | Date Completed
1 | PSEMP delivery date is impacted by delay in FDOT review of the PSEMP skeleton submitted by SwRI. | / | Robert Heller | 2018-04-06 | Schedule | PSEMP delivery date slipped 7 days. | Tushar Patel | 2018-04-06 |  | Closed
2 | Change references to project from Integrated Corridor Management System to Regional Integrated Corridor Management System | 2018-04-09 | Robert Heller |  | Scope | As stated | Tushar Patel | 2018-04-09 |  | Closed
3 | Change Document Identifier from ICMS-XXXX-YYYY to R-ICMS | 2018-04-09 | Robert Heller |  | Scope | As stated | Tushar Patel | 2018-04-09 |  | Closed
4 | Change Monthly Status Report identifier to R-ICMS-MSR-YYMM | 2018-04-09 | Robert Heller |  | Scope | As stated | Tushar Patel | 2018-04-09 |  | Closed
5 | Deliverables will be posted to FDOT Project SharePoint Site and attached to emails for deliveray. | 2018-03-26 | Robert Heller |  | Scope | As stated | Tushar Patel | 2018-03-26 |  | Closed
6 | Question about whether viewing access to data on the user interface needs to be filtered by permission. | 2018-06-15 | Clay Weston |  | Scope | Decision made that if viewer has access to a datasource then they will be able to see all data regardless of agency/ownership/etc. | Clay Packard | 2018-06-15 |  | Closed
7 | Question whether it is desired to have notification by data type and time ranges be configurable per user? Example, for weather alerts, should users be able to turn these off? Requirements don't cover this functionality. | 2018-06-22 | Angela Bos |  | Scope | It is desireable to have each user be able to modifiy notification parmaters, including date and time and type. Users come from multiple different agencies each having different hours of operation, interests in types, and they will want that ability to customize what can be a very distracting and annoying feature (notifications) | Clay Packard | 2018-08-30 |  | Closed
8 | Using All Roads for source of roadway links. | 2018-07-11 | Clay Packard |  | Scope | Using All Roads Basemap with RCI | Jeremy Dilmore | 2018-07-11 |  | Closed
9 | Use HCS7 for SOT Optimization engine; architect the system in a way that it will be feasible to build a similar "synchro driver" under a future ECO | 2018-08-23 | Clay Packard |  | Scope | HCS7 (Synchro in future) | Jeremy Dilmore | 2018-08-23 |  | Closed
10 | Intersection approach volumes come from ITSIQA | 2018-08-23 | Clay Packard |  | Schedule | Intersection approach volumes come from ITSIQA | Clay Packard | 2019-01-02 |  | Closed
11 | Turning movements counts source needs to be determined | 2018-08-23 | Clay Packard | 2018-10-15 | Schedule | use ITSIQA for turning movement counts | Jeremy Dilmore | 2018-08-23 |  | Closed | [8 empty] | Monthly
12 | Iteration 1 will use DMS data instead of ITSIQA data as demontrated dynamic data source | 2018-07-31 | Robert Heller | 2018-08-15 | Schedule | Iteration 1 will use DMS data as dynamic data source instead of ITSIQA data. | Tushar Patel | 2018-08-15 |  | Closed | 9 |  |  |  |  | Update iteration 1 design for DMS instead of ITSIQA | SwRI
13 | Question: will the signal inventory app database be seeded with intersection name and location data? If not, then all map views that show signals will only include those which have been added to the inventory. E.g. response plan view, signals/intersections map layer, SOT corridors | 2018-09-25 | Angela Bos |  |  | Signal inventory app (in development) will be the sole source of intersection and signal location information for anything displayed on RICMS map views. It will not be seeded, data will be added over time by field surveys. | Clay Packard | 2018-09-25 |  | Closed
14 | Use DMS as dynamic data source in Iteration 1 instead of ITSIQA data. | 2018-08-08 | Robert Heller |  | Scope | Approved. | Tushar Patel | 2018-08-09 |  | Closed
15 | If Data Source goes down, maintain the icons on the map in an "unknown" state | 2018-11-06 | Clay Packard |  | N/A | Agreed. | Clay Packard | 2018-11-06 |  | Closed
16
17
18
19
20 | [19 empty] | This is largely unknown until somebody looks at the data.
21
22
23
24
25
41
42
43
44
45
46
47
48
49
50
51
52 |  | Clay P. or Matt J.?
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
iVDS goes away in June to be replaced by DIVAS. Needed for video for GUI when camera icon is clicked Clay 1/29/2019> Discussed with Clint Smith (the new Russell Allen, the PM of DIVAS). It is earlier in the process than documentation has been developed. Let's check back in April 2019 This was discussed on 4/8> We may be able to get the CCTV's remote URL from databus's CCTV stream that's already being ingested, and open that URL from the HTML5 browser directly. To be investigated.
Clay to book a meeting with Mongo, Claudia, and Jeremy and/or Tushar to discuss a more favorable pricing model than linear.
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | 2019-06-04 | Email |  | Heller | Patel / Dilmore | No
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | 2019-06-14 | Email |  | Heller | Patel / Packard | No

## Communication Log
Communications Log
Project |  | Regional Integrated Corridor Management System |  |  | Project # |  |  | BE521
Project Manager |  | Tushar Patel |  |  | Sponsor |  |  | FDOT District 5 Traffic Operations
R&C Level |  | 2 |  |  | Worksheet Updated |  |  | 2019-07-01
ID | Document Title | Description | Date Sent | Format / Method | Template Used | Owner | Recipient/ Attendees | Feedback Expected? | Date Feedback Due | Date Feedback Received
1 | PSEMP Template | Skeleton for review and approval by FDOT | 2018-03-21 | email of .docx |  | Heller | Tushar Patel | Yes | 2018-03-31 | 2018-04-06
2 | ICMS-MTG-Agenda-Kickoff-2018-04-03 | Project Kickoff Meeting Agenda | 2018-03-26 | email .docx & .pdf | NA | Heller | Patel / Packard | No
3 | Kickoff Meeting Slides | Sans high level schedule | 2018-03-30 | email .pptx & pdf | NA | Heller | Patel / Packard | No
4 | Kickoff Meeting Slides Update | Included high level schedule | 2018-04-02 | email pptx and pdf | NA | Heller | Patel / Packard | No
5 | ICMS-MSR-1803 | Monthly status report for March 2018 | 2018-04-05 | sharepoint post | NA | Heller | Patel / Packard / Dilmore | No
6 | R-ICMS-MSR-1803 | Monthly Status Report for March 2018 | 2018-04-05 | Email |  | Heller | Patel / Packard / Dilmore | No
7 | R-ICMS-MTG-Minutes-Kickoff-2018-04-03 | Kickoff meeting minutes | 2018-04-09 | sharepoint post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-04-23 | 2018-04-13
8 | R-ICMS-ASTLog-0.1 | Risk Register | 2018-04-13 | Sharepoint Post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-04-27 | OBE
9 | R-ICMS-SCHED-0.1 | Project Schedule DRAFT | 2018-04-13 | Sharepoint post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-04-20 | OBE
10 | R-ICMS-MTG-AGENDA-RQT Walkthrough-2018-04-23 | Draft Agenda for the Requirements Walkthrough | 2018-04-16 | Sharpoint Post | NA | Heller | Patel / Packard / Dilmore | No
11 | R-ICMS-MTG-Minutes-KIckoff-2018-04-03-0.2 | Kickoff meeting minutes resubmittal IAW comments | 2018-04-20 | sharepoint post | NA | Heller | Patel / Packard / Dilmore | No
12 | R-ICMS-PSEMP-0.1 | Project Systems Engineering Management Plan | 2018-04-20 | sharepoint post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-05-04 | OBE
13 | R-ICMS-SCHED-0.1 Delay Delivery | Requested 1 week delay in delivery of updated schedule and response from Patel confirming delay | 2018-04-23 | Email | NA | Heller | Tushar Patel / Robert heller | No
14 | R-ICMS-REQ-0.1T | System Requirements Specification Template | 2018-04-26 | Sharepoint Post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-04-10 | OBE
15 | R-ICMS-SCHED-0.2 | Project Schedule Revised IAW FDOT Comments. | 2018-05-01 | Sharepoint Post | NA | Heller | Patel / Packard / Dilmore | Yes | 2018-05-06 | 2018-05-02
16 | BE521 R-ICMS-MSR-1804 Monthly Status Report for April 2018 | Monthly Status Report | 2018-05-03 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | No
17 | R-ICMS-MSR-1804 | Monthly Status Report for April 2018 | 2018-05-03 | Email |  | Heller | Patel / Packard / Dilmore | No
18 | R-ICMS-REQ-0.1T System Requirements Specification for R-ICMS Template | Systems Requirements Specification Template | 2018-05-03 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | Yes | 2018-05-17 | OBE
19 | R-ICMS-SDP-0.1t | SDP Template | 2018-05-03 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | Yes | 2018-05-17 | OBE
20 | BE521 R-ICMS-PSEMP-1.0, R-ICMS-ASTLog-1., R-ICMS-Sched-1.0 | Risk Register | 2018-05-04 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | No |  |  | This is largely unknown until somebody looks at the data.
21 | BE521 R-ICMS Request for Highway Capacity Software (HCS7 | Formal request for access to HCS7 Software | 2018-05-10 | Email |  | Heller | Patel / Packard / Dilmore | No
22 | BE521 SwRI 23368 R-ICMS-REQ-0.1-docx & R-ICMS-REQ-0.1.xlsx Delivery of Software Requirements Specification.- | Requirements Spcificiation Version 0.1 | 2018-05-14 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | Yes | 2018-05-28 | OBE
23 | BE521 R-ICMS-SDP-0.1 Software Development Plan. | Software Development Plan | 2018-05-25 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | Yes | 2018-06-08 | 2018-06-01
24 | BE521 SwRI 23368 R-ICMS-REQ-0.2-docx & R-ICMS-REQ-0.2.xlsx Delivery of Software Requirements Specification | Requirements Spcificiation Version 0.2 Lacks SOT | 2018-05-25 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | 2018-11-16 | 2018-05-09 | OBE
25 | R-ICMS-MTG-AGENDA-SOT Workshop-20180606 | Meeting Agenda for the SOT Workshop | 2018-05-31 | Sharepoint Post | NA | Heller | Patel / Packard / Dilmore | No
26 | R-ICMS-MTG-AGENDA-SOT Workshop-20180606 | Agenda for SOT requirements workshop | 2018-05-31 | Sharepoint post |  | Heller | Patel / Packard / Dilmore | No
27 | R-ICMS-MSR-1805 | Monthly Status Report for May 2018 | 2018-06-04 | Email |  | Heller | Patel / Packard / Dilmore | No
28 | Signal Retiming and SOT Workflow v1.docx | Minutes from SOT Requriements workshop | 2018-06-06 | Email |  | Clay Packard |  | No
29 | BE521, SwRI 23368 R-ICMS-CG-0.1 Software Coding Guidelines | Software Coding Guidelines | 2018-06-12 | Sharepoint Post |  | Heller | Patel / Packard / Dilmore | Yes | 2018-06-26 | 2018-06-20
30 | Access to FDOT SunGuide Source Code. | Formal Request for access to SunGuide Source Code | 2018-06-18 | Email |  | Heller | Patel / Packard / Dilmore | Yes |  | 2018-06-21
31 | R-ICMS-Agenda-PDR-20180626 | Preliminary Design Review Agenda | 2018-06-18 | email |  | Heller | Patel / Packard / Dilmore | No
32 | R-ICMS-MTG-SLIDES-PDR-20180625 | Presentation Materials for PDR. | 2018-06-25 | Email Sharepoint Post |  | Heller | Patel / Packard / Dilmore | No | 2018-06-25
33 | R-ICMS-PD-0.1.docx | Preliminary Design Document | 2018-06-25 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | Yes | 2018-07-09 | 2018-07-02
34 | R-ICMS-MSR-1806.docx | Monthly Status Report for June 2018 | 2018-07-05 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No
35 | R-ICMS-REQ-0.1.xlsx SOT | SOT Revised Requirements | 2018-07-05 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No
36 | R-ICMS-SDP-0.2.docx | Software Development Plan Revision | 2018-07-05 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | Yes | 2018-07-19 | 2018-07-05
37 | R-ICMS-SDP-1.0 docx | Software Development Plan Final | 2018-07-06 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No
38 | NA | Permission to subcontract to McTrans Center at UF | 2018-07-17 | Email |  | Heller | Patel | Yes | 2018-07-31 | OBE
39 | R-ICMS-PDD-0.2 | Preliminary Design Document Revision 2 | 2018-07-19 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | Yes | 2018-08-02 | OBE
40 | R-ICMS-MTG-AGENDA-20180731 | Iteration #1 Detailed Design Review Agenda | 2018-07-24 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No
41 | NA | Request to reference project | 2018-07-27 | Email |  | Heller | Patel | Yes |  | OBE
42 | R-ICMS-SDD-0.1.docx | Software Design Document for Iteration 1 | 2018-07-31 | Email Sharepoint |  | Heller | FDOT & Consultants | Yes | 2018-08-14 | 2018-08-23
43 | R-ICMS-MSR-1807.docx | Monthly Status Report for July 2018 | 2018-08-06 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No | 2018-08-13 | 2018-08-13
44 | Synchro Input Files / HCS 7 Sample Files | HSC7 Input File Sample | 2018-08-14 | Email |  | Packard | Bos / Vickers | No
45 | Synchro File Corridor | Synchro File for Corridor | 2018-08-15 | Email |  | Packard | Bos / Vickers | No
46 | ETL code projects for AAM Dashboard and SunRail GTFS-RT | Clay P. or Matt J.? | 2018-08-23 | Email |  | Packard | Weston / Bos / Cherukuri / Miller | No
47 | R-ICMS-SDD-0.1 Comments | Comments from FDOT on R-ICMS-SDD-0.1.docx | 2018-08-23 | Email |  | Packard | Heller | No
48 | SOT R-ICMS-REQ-0.3.1.xlsx | SOT revised requirements | 2018-08-27 | Email |  | Heller | Packard / Miller / Juckes | Yes |  | OBE
49 | ITSIQA DRAFT SDD | ITSIQA DRAFT SDD includes ICD for data access | 2018-08-30 | Email |  | Packard | Heller / Weston | No
50 | R-ICMS-MSR-1808.docx | Monthly Status Report for August 2018 | 2018-08-31 | Email Sharepoint |  | Heller | Patel / Packard / Dilmore | No | 2018-09-12 | 2018-09-12
51 | SOT R-ICMS-REQ-0.3.1.xlsx Comments | Response to proposed SOT requirements | 2018-09-06 | Email |  | Packard | Heller | No
52 | SunGuide Source Code Reuse Permission | Restatement of Derek Vollmer Permission to Reuse SunGuide Source Code for R-ICMS project | 2018-09-12 | Email |  | Packard | Heller | No
53 | R-ICMS-STP-0.1T.docx | STP Template for Approval | 2018-09-18 | Email Sharepoint |  | Weston | Patel / Packard / Dilmore | Yes | 2018-10-02 | 2018-09-19
54 | R-ICMS-STP-0.2T.docx | STP Template for Approval | 2018-09-18 | Email Sharepoint |  | Weston | Patel / Packard / Dilmore | Yes | 2018-10-02 | 2018-09-20
55 | R-ICMS-STP-1.0T.docx | STP Template Approved | 2018-09-20 | Email Sharepoint |  | Weston | Patel / Packard / Dilmore | No
56 | Report-Iteration-1-Requirements-23-Sep-2018.xlsx | Iteration 1 Requirements | 2018-09-23 | Email |  | Weston | Patel / Packard | No
57 | R-ICMS-SDD-0.2.docx | Software Detail Design Iteration 1 Revised | 2018-09-24 | Email Sharepoint |  | Weston | Patel / Packard / Dilmore / Miller / Juckes | Yes | 2018-10-08 | OBE
58 | R-ICMS-SDD-0.2.docx Comments | Review of R-ICMS-SDD-02.docx Comments | 2018-10-01 | Email |  | Packard | Weston | No
59 | R-ICMS-MSR-1809 | Monthly Status Report for September 2018 | 2018-10-03 | Email |  | Heller | Patel / Packard / Dilmore | No
60 | R-ICMS-SDD-0.3 | Software Detail Design Iteration 1 | 2018-10-05 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-10-19 | 2018-10-10
61 | R-ICMS-STP-0.1T.docx | System Test Plan Template Proposed | 2018-10-15 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-10-29 | OBE
62 | R-ICMS-SDD-0.3 | Software Detail Design Iteration 1 | 2018-10-16 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-10-30 | 2018-10-30
63 | R-ICMS-STP-1.0 System Test Plan | Approved System Test Plan | 2018-10-16 | Email |  | Weston | Patel / Packard / Dilmore | No |  | 2018-10-10
64 | R-ICMS-TPD-0.1T | Test Procedures Document Template Proposed | 2018-10-19 | Sharepoint Site |  | Weston | Patel / Packard / Dilmore | Yes | 2018-11-02 | OBE
65 | R-ICMS-REQ-1.0 | System Requirements Specification Approved | 2018-10-22 | Email |  | Weston | Patel / Packard / Dilmore | No
66 | R-ICMS-VDD-0.1T | Version Description Document Template Proposed | 2018-10-23 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-11-06 | 2018-12-11
67 | R-ICMS-MTG-AGENDA-TRR1-20181106 | Test Readiness Review Iteration 1 Agenda includes actual FAT | 2018-10-26 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-11-09 | 2018-10-26
68 | R-ICMS-TPD-0.1 | Test Procedures Document Iteration 1 | 2018-10-29 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2018-11-12 | 2018-10-30
69 | R-ICMS-MTG-AGENDA-20181106 | Test Readiness Review Iteration 1 Agenda includes actual FAT UPDATED | 2018-10-30 | Email |  | Weston | Patel / Packard / Dilmore | No
70 | R-ICMS-SDD-1.0 | Software Design Document for Iteration 1 Approved | 2018-10-30 | Sharepoint Site |  | Weston | Patel / Packard / Dilmore | No
71 | ITISQA-Detailed Design - V1.7 - 2018-10-31 | ITSIQA design document including the output ICD. | 2018-10-31 | Email |  | Packard | Weston / Heller | No
72 | R-ICMS-MSR-1810 | Monthly Status Report for October 2018 | 2018-11-14 | Email |  | Heller | Patel / Packard / Dilmore | No
73 | R-ICMS-MSR-1811 | Monthly Status Report for November 2018 | 2018-12-06 | Email |  | Heller | Patel / Packard / Dilmore | No
74 | R-ICMS-STR-0.1 | Software Test Report Iteration 1 | 2018-12-10 | Email |  | Heller | Patel / Packard / Dilmore | Yes | 2018-12-24 | 2019-01-02
75 | Invoice FY19-038615 | Invoice for the Requirements Analysis Milestone | 2018-12-17 | Email |  | SwRI Accounts Receivable | Patel | No
76 | R-ICMS-MSR-1812 | Monthly Status Report for December 2018 | 2019-01-07 | Email |  | Heller | Patel / Packard / Dilmore | No
77 | R-ICMS-STR-0.2 | Regional Integrated Corridor Management System Software Test Report Revision | 2019-01-11 | Email |  | Heller | Patel / Packard / Dilmore | Yes | 2019-01-25 | 2019-04-15
78 | R-ICMS-Agenda-CDR-2-20190115.docx | Draft Agenda for Critical Design Iteration 2 | 2019-01-15 | Email |  | Weston | Patel / Packard / Dilmore | No
79 | R-ICMS-SDD-1.1 | Software Design Document Version 1.1 Iteration 2 | 2019-01-16 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2019-02-08 | 2019-03-19
80 | R-ICMS-CDR2-Slides | Powerpoint slides for Critical Design Iteration 2 | 2019-01-21 | Email |  | Weston | Patel / Packard / Dilmore | No
81 | R-ICMS-VDD-0.1 | Version Description Document DRAFT | 2019-02-04 | Email |  | Weston | Patel / Packard / Dilmore | Yes | 2019-02-18 | 2019-02-20
82 | R-ICMS-MSR-1901 | Monthly Status Report for January 2019 | 2019-02-05 | Email |  | Heller | Patel / Packard / Dilmore | No
83 | R-ICMS-MSR-1901 | Monthly Status Report for January 2019 | 2019-02-05 | Email |  | Heller | Patel / Packard / Dilmore | No
84 | R-ICMS-MSR-1902 | Monthly Status Report for February 2019 | 2019-03-05 | Email |  | Heller | Patel / Packard / Dilmore | No
85 | R-ICMS-VDD-1.0 | Version Description Document Approved | 2019-03-12 | Email |  | Heller | Patel / Packard / Dilmore | Yes | 2019-03-26 | 2019-04-01
86 | R-ICMS-SDD-1.2 | Software Design Document Version 1.2 Iteration 2 in response to FDOT comments. | 2019-04-03 | email |  | Heller | Patel / Packard / Dilmore | Yes | 2019-04-17 | 2019-04-04
87 | R-ICMS-VDD-1.0 | Version Description Document for Iteration 1 Final | 2019-04-03 | Email |  | Heller | Patel / Packard / Dilmore | No
88 | R-ICMS-MSR-1903 | Monthly Status Report for March 2019 | 2019-04-05 | Email |  | Heller | Patel / Packard / Dilmore | No
89 | SwRI Invoice FY19-089695 | SwRI Invoice for Design Validation | 2019-04-13 | Email |  | SwRI Accounts Receivable | Patel / Dilmore | Yes |  | 2019-04-15
90 | R-ICMS-STR-1.0 | Software Test Report Iteration 1 Final | 2019-04-15 | Email |  | Heller | Patel / Packard / Dilmore | No
91 | R-ICMS-TPD-1.0 | Software Test Procedures Iteration 1 Final. | 2019-04-15 | Email |  | Heller | Patel / Packard / Dilmore | No
92 | R-ICMS-SSSC-1.0 | Software System Source Code | 2019-04-17 | Email |  | Heller | Patel / Packard / Dilmore | No
93 | R-ICMS-Technical Report | R-ICMS Proposed Production HW and SW Configuration | 2019-04-17 | Email |  | Heller | Patel / Packard / Dilmore | Yes | 2019-05-01 | 2019-04-24
94 | SwRI Invoice FY19-098439 | SwRi Invoice for Design Validation Resubmittal | 2019-04-23 | Email |  | Heller | Patel / Dilmore | No
95 | ECP-01 | Engineering Change Proposal 01 - Creating Uni-Directional Roadway Links from ARBM Bi-Directional Links | 2019-04-24 | email |  | Heller | Patel / Packard | Yes | 2019-05-08 | 2019-04-30
96 | R-ICMS-MSR-1904 | Monthly Status Report for April 2019 | 2019-05-06 | Email |  | Heller | Patel / Packard / Dilmore | No
97 | ECP-01 Further Justification | Engineering Change Proposal 01 - Creating Uni-Directional Roadway Links from ARBM Bi-Directional Links | 2019-05-08 | Email |  | Heller | Patel / Packard | Yes | 2019-05-22 | 2019-05-22
98 | R-ICMS-MSR-1905 | Monthly Status Report for May 2019 | 2019-06-05 | Email |  | Heller | Patel / Packard / Dilmore | No
99 | SwRI Invoice FY19-098439 | SwRI Invoice for Iteration 1 (Design Validation Milestone) | 2019-06-04 | Email |  | Heller | Patel / Dilmore | No
100 | R-ICMS-STP-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT System Test Plan R-ICMS-STP-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17 | 2019-06-17
101 | R-ICMS-TPD-1.1 | Regional Integrated Corridor Management System Iteration 2 DRAFT Test Procedures Document R-ICMS-TPD-1.1 | 2019-06-06 | Email |  | Heller | Patel / Packard | Yes | 2019-06-17 | 2019-06-17
102 | ICMS-MTG-NOTES-TRR-2019-06-13 | Slides and notes from Test Readiness Review R-ICMS-Slides+Notes-TRR-2.0 | 2019-06-14 | Email |  | Heller | Patel / Packard | No
103 | R-ICMS-MSR-1906 | Monthly Status Report | 2019-07-05 | Email |  | Weston | Patel / Packard | No
104 | R-ICMS-MSR-1907 | Monthly Status Report | 2019-08-05 | Email |  | Weston | Patel / Packard | No
105 | R-ICMS-MSR-1908 | Monthly Status Report | 2019-09-05 | Email |  | Weston | Patel / Packard | No
106 | R-ICMS-MSR-1909 | Monthly Status Report | 2019-10-05 | Email |  | Weston | Patel / Packard | No
107 | R-ICMS-MSR-1910 | Monthly Status Report | 2019-11-05 | Email |  | Weston | Patel / Packard | No
108 | R-ICMS-MSR-1911 | Monthly Status Report | 2019-12-05 | Email |  | Weston | Patel / Packard | No
109 | R-ICMS-MSR-1912 | Monthly Status Report | 2020-01-05 | Email |  | Weston | Patel / Packard | No
110 | R-ICMS-MSR-2001 | Monthly Status Report | 2020-02-05 | Email |  | Weston | Patel / Packard | No
111 | R-ICMS-MSR-2002 | Monthly Status Report | 2020-03-05 | Email |  | Weston | Patel / Packard | No
112 | R-ICMS-MSR-2003 | Monthly Status Report | 2020-04-05 | Email |  | Weston | Patel / Packard | No
113 | R-ICMS-MSR-2004 | Monthly Status Report | 2020-05-05 | Email |  | Weston | Patel / Packard | No
114 | R-ICMS-MSR-2005 | Monthly Status Report | 2020-06-05 | Email |  | Weston | Patel / Packard | No
115 | R-ICMS-MSR-2006 | Monthly Status Report | 2020-07-05 | Email |  | Weston | Patel / Packard | No
116 | R-ICMS-MSR-2007 | Monthly Status Report | 2020-08-05 | Email |  | Weston | Patel / Packard | No
117 | R-ICMS-MSR-2008 | Monthly Status Report | 2020-09-05 | Email |  | Weston | Patel / Packard | No
118 | R-ICMS-MSR-2009 | Monthly Status Report | 2020-10-05 | Email |  | Weston | Patel / Packard | No
119 | R-ICMS-MSR-2010 | Monthly Status Report | 2020-11-05 | Email |  | Weston | Patel / Packard | No
120 | R-ICMS-MSR-2011 | Monthly Status Report | 2020-12-05 | Email |  | Weston | Patel / Packard | No
121 | R-ICMS-MSR-2012 | Monthly Status Report | 2021-01-05 | Email |  | Weston | Patel / Packard | No
122 | R-ICMS-MSR-2101 | Monthly Status Report | 2021-02-05 | Email |  | Weston | Patel / Packard | No
123 | R-ICMS-MSR-2102 | Monthly Status Report | 2021-03-05 | Email |  | Weston | Patel / Packard | No
124 | R-ICMS-MSR-2103 | Monthly Status Report | 2021-04-05 | Email |  | Weston | Patel / Packard | No
125 | R-ICMS-MSR-2104 | Monthly Status Report | 2021-05-05 | Email |  | Weston | Patel / Packard | No
126 | R-ICMS-MSR-2105 | Monthly Status Report | 2021-06-05 | Email |  | Weston | Patel / Packard | No
Formulas:
Date Feedback Due = [Date Sent]+14

## Change Request Form
Change Control Request Form
Project | Regional Integrated Corridor Management System | Project # | BE521
Project Manager | Tushar Patel | Sponsor | FDOT District 5 Traffic Operations
R&C Level | 2 | Worksheet Updated | 2018-05-02
CHANGE CONTROL REQUEST FORM
Project |  | #
Project Manager |  | R&C Category
Project Sponsor
Change Control #
Requested by |  | Date
Primary Nature of Change | Scope |  | Quality
| Schedule |  | Cost
Description of Change
Reason for Change
Benefits of Change
Implications of not making change
Impact | Explain Impact in Detail
Scope
Schedule
Cost
Quality
Resources
Requirements (Specify #)
Other
Planned Implementation Date for Change:
Contract Amendment Needed? | Yes / No | Person Responsible
Change Approved | Yes / No | Conditions for Approval / Reason For Denial
Change Denied
Signatures
Project Manager
Project Sponsor
(add others as necessary)
Documents Updated On:
Documents Updated by:
Contract Amendment #